## INTRODUCTION
Green Star Buildings
Green Star Buildings
Credit 4 | Responsible Resource Management
Outcome | Operational waste and recovery streams can be separated and recovered in a safe and efficient manner.
Criteria | There are two pathways available in this credit: a ‘Performance Pathway’ that relies on specialised waste management solutions, or a ‘Prescriptive Pathway’ that outlines specific best practice requirements. Performance Pathway: Specialist Plan A qualified waste auditor or waste specialist prepares and implements an Operational Waste Management Plan (OWMP) for the project in accordance with best practice approaches and this is reflected in the building’s design. Prescriptive Pathway: Facilities The building is designed for the separation of waste and recovery streams, provides a dedicated and adequately sized waste storage area(s), and ensures safe and efficient access to the waste storage area(s) for both occupants and the waste and recovery collection contractors. A waste specialist or waste contractor must sign off on the final design and provide confirmation that the proposed operational waste management system utilised to inform the final design is accurate and correct.
Requirements: Minimum Expectations
Performance Pathway: Specialist Plan |  | The project must comply with the two following criteria if the Performance Pathway is followed: - Preparation and Implementation of Operational Waste Management Plan (OWMP) - OWMP prepared by qualified waste auditor or waste specialist
Prescriptive Pathway: Facilities |  | The project must comply with the four following criteria if the Prescriptive Pathway is followed: - Separation of waste and recovery streams - Dedicated waste storage area(s) - Access to waste storage area(s) - Final sign-off by waste specialist or waste contractor is required
NZGBC Operational Waste Calculator v1.0
Purpose | Provide a process for calculating an appropriately sized waste storage area. This process has been created to mainly support Prescriptive Pathway submissions, but they can be utilised to support a Performance Pathway submission.
Function | User to complete the following worksheets:
WASTE CALCULATOR Calculate the expected volume of waste and recovery streams per week for a building
SEPARATION Confirm that the waste and recovery services (including bin sizes, bin counts and collection frequency) meet / exceed the calculated weekly volume
STORAGE Calculate the preliminary floor area (m2) of an adequately sized waste storage area based on the waste and recovery services
Support | User is provided additional supporting information on the following worksheets:
ACCESS Information on collection vehicles and operating dimensions to be utilised to confirm suitable access is provided
DESIGN Information on elements to consider when designing a waste storage area
DATA High-level information on the data that feeds into the calculations used to create the NZGBC Operational Waste Calculator v1.0
FAQ Some frequently asked questions raised by professionals and experts during the development of the NZGBC Operational Waste Calculator v1.0

## GUIDE
Guidelines
This section provides guidance on how to use the NZGBC Operational Waste Calculator v1.0.
Function
The core function of the NZGBC Operational Waste Calculator v1.0 is to provide a methodology to calculate the floor area of an adequately sized primary waste storage area.
Methodology
This methodology follows 3 logical steps:
Step 1 | WASTE CALCULATOR: Calculate the expected volume of waste and recovery streams per week for a building
There are two suitable methods to calculate the expected waste volumes to be generated from the building once it is fully operational: Method 1: Real-World Historical Data - This is the preferred method as it utilises the most relevant data to your building - e.g. If you know the tenant of your new industrial building, utilising real-world data from other facilities operated by this tenant would be the best option Follow the instructions on the WASTE CALCULATOR sheet, and fill in the following blue cells: Building typology GFA of building General waste (L/week) Recycling (L/week) Food waste (L/week) The total waste (L/week) will automatically be calculated. If you utilise Method 1, the values will automatically pull through into the SEPARATION sheet and be displayed in the Volume Required (L/week) column. If you only have real-world data for the total waste (L/week) and no split between general waste, recycling and food waste, you can utilise the following split: General waste - 30% Recycling - 62% Food Waste - 8% For more information on this, view the DATA sheet.
Method 2: Waste Generation Rates from NZGBC Operational Waste Calculator v1.0 - This is the option to utilise if no suitable data is available - e.g. If you do not know the tenant of your new industrial building, utilising the Industrial building typology waste generation rate from waste calculator would be a suitable option Follow the instructions on the WASTE CALCULATOR sheet, and fill in the relevant blue cells assocaited with the GFA for your building / development: Enter the GFA of applicable building typology or building typologies (m2) The waste volume calculations will automatically be calculated. These values will automatically pull through into the SEPARATION sheet and be displayed in the Volume Required (L/week) column. Note: The formula in the SEPARATION sheet prioritises Method 1, so if you you enter data in both sections, the Method 1 data will be displayed in the SEPARATION sheet.
Step 2 | SEPARATION: Confirm that the waste and recovery services (including bin sizes, bin counts and collection frequency) to meet / exceed the calculated weekly volume
Refering to the SEPARATION sheet, confirm the following services or systems will be implemented by filling in the blue cells: Minimum Expected Streams - Confirm the service per material, and confirm compliance by choosing 'YES'. Minimum Expected Systems - Confirm the system per material, and confirm compliance by choosing 'YES'. Additional Streams - Where applicable, confirm any additional materials and the service that will manage it. Review the Bin Types section. The most common bin types and sizes are provided. If the exact bin type and size combination used for the building is not shown by default, fill in the actual size (L) into the applicable blue cells. If the type of bin is not on the list, or no bin will be used (i.e. bale), then manually provide a size (L) under the Other bin type. The waste services (bin size, bin count and collection frequency) must meet or exceed the calculated weekly volume of waste and recoverables. Calculated volume of waste and recoverables ≤ [bin volume] × [bin count] x [collection frequency] To confirm complaince, complete the table at the bottom of the SEPARATION sheet. Fill in the recycling services Choose the applicable Bin Code Choose the applicable Bin Size (these are linked to the Bin Code, and will provide options based on the Bin Sizes table) Fill in the Bin Count Fill in the Collections/week The Volume Serviced (L/week) will be automatically calculated, and if this is equal to or exceeds the Volume Required (L/week), a YES will be shown, confirming compliance. If a NO is shown, then the waste services will need to be tweaked until compliance is confirmed.
Step 3 | STORAGE: Calculate the preliminary floor area (m2) of an adequately sized waste storage area based on the waste and recovery services
Refering to the STORAGE sheet, the first section shows the Bin Dimensions. This table provides the dimensions and floor area of the most common bin types. If you have entered a custom bin size in the SEPARATION sheet, the size (L) will automatically pull through into the table, but you are required to manually enter the dimensions (Depth, Width, Height) for that custom bin in the blue cells provided. The floor area of that bin will be automatically calculated. Finally, utilise the Waste Area Size section to calculate the Preliminary Total Floor Area (m2) for the waste storage area. Choose the applicable Bin Code Choose the applicable Bin Size Note: The Floor Area (m2) for a single bin combination will be automaically provided. Fill in the Bin Count The Total Floor Area (m2) per bin combination will be automatically calculated. The Total Bin Floor Area (m2) for all the bins will be automatically calculated. Indicative floor area for bin manoeuvres and access will be automatically calculated, noting this is equal to the Total Bin Floor Area. The Preliminary Total Floor Area (m2) for the entire waste storage area will be automatically calculated. To confirm preliminary compliance, fill in the floor area of the proposed waste storage area from the building's designs. The designed waste area should be equal to or exceed the preliminary total floor area calculated. If it does, Preliminary Compliance will be confirmed by a YES.

## WASTE CALCULATOR
Waste Calculator
To determine the preliminary total floor area (m2) of an adequately sized waste storage area, you must first calculate the expected volume of waste and recovery streams per week for a building.
Weekly Waste Volumes
There are two suitable methods to calculate the expected waste volumes to be generated from the building once it is fully operational: Method 1: Real-World Historical Data - This is the preferred method as it utilises the most relevant data to your building - e.g. If you know the tenant of your new industrial building, utilising real-world data from other facilities operated by this tenant would be the best option Method 2: Waste Generation Rates from NZGBC Operational Waste Calculator v1.0 - This is the option to utilise if no suitable data is available - e.g. If you do not know the tenant of your new industrial building, utilising the Industrial building typology waste generation rate from waste calculator would be a suitable option
Method 1: Real-World Historical Data
The utilisation of real-world historical data is the preferred option, as it will provide waste data that is relevant and accurate to your building's exact requirements. To be suitable, the following conditions should be met: - at least 12 months of data - the chosen dataset must come from a building or development of the same typology as your new building - the dataset must provide waste and recycling data by weight (kilograms or tonnes) or by volume (litres or cubic metres) The historical data must be normalised to provide a calculated waste volume for the new building. This must be done in a logical way, with some examples stated below: - building footprint (m2): data from a 5,000m2 distribution warehouse should be x2 if the new distribution warehouse is 10,000m2 - occupancy (people / bedrooms / units): data from a hotel with a capacity of 100 occupants should be x1.25 if the new hotel has a capacity of 125 occupants - output (products, tonnage): data from a manufacturing facility producing 100t of product/week should be x3 if the new manufacturing facility can produce 300t of product/week The above are examples, and any realistic or logical normalisation of the data is acceptable, so long as justification is provided. Once normalised, filter the data to show the litres of waste per week per waste type. If your data provides weight and not volume information, you can use the DATA sheet provided to convert to volume (as the bin setup is based on volume). Instruction: Fill in the below blue fields only if you have historical data, otherwise skip to Method 2 below.
Building Typology | GFA (m2) | Total Waste (L/week) | General Waste (L/week) | Recycling (L/week) | Food Waste (L/week)
If you have chosen General/Other or the building is a mix of different Typologies please provide a description below
Method 2: Waste Generation Rates from NZGBC Operational Waste Calculator v1.0
Utilising data from a variety of New Zealand commercial buildings, the below calculator has been created to provide an estimated total volume of waste (litres) to be generated per week for different building typologies. Once the total volume of waste has been calculated, audit data has been utilised to provide the split between general waste (30%), recycling (62%) and food waste (8%).
Instruction: Fill in the GFA (m2) of the building in the blue cells below, noting this must include all areas - Different building typologies have different waste generation rates, so choose the correct option(s) carefully - If you have a mixed-use building, or a building where you can accurately split floor space between multiple typologies, you can split the total floor space between these different typologies to make your calculation more accurate - If your building typology is not an option, chose the General / Other typology
Building Typology | GFA (m2) | Total Waste (L/week) | General Waste (L/week) | Recycling (L/week) | Food Waste (L/week)
Hotel / Accommodation |  | 0 | 0 | 0 | 0
Aged Care |  | 0 | 0 | 0 | 0
Office / Admin |  | 0 | 0 | 0 | 0
Industrial |  | 0 | 0 | 0 | 0
Retail |  | 0 | 0 | 0 | 0
Supermarket |  | 0 | 0 | 0 | 0
General / Other |  | 0 | 0 | 0 | 0
Total |  | 0 | 0 | 0 | 0
The calculated weekly total waste volumes will automatically be included in the SEPARATION sheet.
Note: The NZGBC acknowledges that generation rates are not available for all building typologies, and that variations in waste generating activities within these typologies are also to be expected as these groups are very broad. To include more typology options and variations, we require more data points. If you are interested and willing to provide data for inclusion within the next version of this calculator, please email greenstarnz@nzgbc.org.nz. All data will be treated as confidential, and utilised for the sole purpose of ensuring our waste generation rate calculator is as accurate and inclusive as possible.

## SEPARATION
Separation
This section is used to confirm that the waste and recovery services (including bin sizes, bin counts and collection frequency) meet / exceed the calculated weekly volume.
Minimum Expected Streams
Instruction: Confirm the services that will manage the following materials by filling in the blue cells below | [8 empty] | Yes/No
Landfill |  |  | General Waste | [6 empty] | YES | NO
Recovery |  |  | Paper
Cardboard
Plastic bottles, trays and containers marked 1/2/5
Glass bottles and jars
Aluminium and steel tins and cans
Note: The recovery materials above are most commonly serviced by a Mixed Recycling collection service. If the Mixed Recycling service in the region does not include some of these materials, a single stream service must be implemented to recover it.
Organics |  |  | Food scraps
Note: Food scraps must be recovered, whether by an on-site solution or a collection service with an off-site solution. Solutions may include composting, vermiculture (worm farms), bioconversion (fly farms), animal feed, anaerobic digestion or any other suitable solution that ensures recovery or conversion of either materials or energy.
Minimum Expected Systems
Instruction: Confirm a system will be put in place to manage the following potentially hazardous materials by filling in the blue cells below
Landfill / Recovery |  |  | Dangerous Goods (DG 1- 9)
Recovery |  |  | Batteries
Printer Cartridges
e-Waste (Electronic Waste)
Note: Hazardous or potentially hazardous materials cannot go into the general waste and can’t be recovered via standard recovery services. It is therefore important to implement a system for these materials to either ensure safe disposal or recovery via an appropriate service. Whether is it expired cleaning chemicals, broken electronics or used batteries, a system must be put in place to ensure these materials are managed safely and do not end up in the general waste.
Additional Streams
It is a minimum expectation to implement at least one additional waste recovery stream and a service for any individual material that totals more than 5% of the development or building’s annual waste profile either by volume (m3) or weight (kg). Some examples of common materials are scrap metal, wooden pallets, clear LDPE shrink wrap and garden waste, but these will be dependant on building typology. Instruction: If applicable, confirm the additional material(s) and the service(s) that will manage them by filling in the blue cells below.
Material Type |  |  |  | Recovery Stream
Bin Types
The most common bins used for operational waste, along with their most common sizes (litres), are shown below. If your local waste contractor uses different sizes, these can be entered into the blue fields.
Bin Types | Bin Code | Common Bin Sizes (L) | [5 empty] | Custom Bin Size (L)
Crate | CRT | 40
Wheelie Bin | MGB | 80 | 120 | 140 | 240 | 660 | 1100
Front End Load | FEL | 1500 | 3000 | 4500
Skip Bin | SKIP | 3000 | 9000
Hook Bin | HOOK | 15000 | 30000
Fadge Bag | FDG | 700
FlexiBin® | FXB | 1000 | 2000 | 3000
Other | OTHER
Confirm Compliance
To confirm compliance, the waste and recovery services (including bin sizes, bin counts and collection frequency) must meet / exceed the calculated weekly volume. i.e. the Volume Serviced (L/week) must equal tor exceed the calculated Volume Required (L/week). Instruction: Fill in the blue cells below with the proposed waste and recovery services for the building. Note: The Volume Serviced (L/week) in column F will be automatically calculated. Ensure you fill in the bin size (litres), the bin count and the frequency of collections per week. The bin size and collection frequency should be confirmed with the local waste contractor to ensure it reflects available services.
Referring to the WASTE CALCULATOR sheet: The Volume Required (L/week) below will automatically be pulled from the WASTE CALCULATOR sheet.
Waste Type | Bin Code | Bin Size (L) | Bin Count | Collections / Week | Volume Serviced (L/week) | Volume Required (L/week) | Compliant | Waste Type Split (Vol%)
General Waste |  |  |  |  | 0 | 0 | YES
0
0
0
Recycling |  |  |  |  | 0 | 0 | YES
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Food Scraps |  |  |  |  | 0 | 0 | YES
0
0
0
Total |  |  | 0 |  | 0 | 0 | YES | 0%

## STORAGE
Storage
This section is used to calculate the preliminary floor area (m2) of an adequately sized waste storage area.
Bin Dimensions
The below table provides the dimensions and floor area of the most common bin types:
If you have entered a custom bin size in the SEPARATION sheet, enter the dimensions in the blue cells below
Bin Types | Bin Code | Size (L) | Depth (m) | Width (m) | Height (m) | Floor Area (m2)
Crate | CRT | 40 | 0.53 | 0.45 | 0.5 | 0.2385
CRT
Wheelie Bin | MGB | 80 | 0.48 | 0.48 | 0.93 | 0.2304
| MGB | 120 | 0.48 | 0.48 | 0.93 | 0.2304
| MGB | 140 | 0.55 | 0.535 | 0.92 | 0.29425
| MGB | 240 | 0.73 | 0.58 | 1.075 | 0.4234
| MGB | 660 | 0.784 | 1.37 | 1.215 | 1.0741
| MGB | 1100 | 1.26 | 1.065 | 1.215 | 1.3419
MGB
Front End Load | FEL | 1500 | 0.95 | 2 | 1.1 | 1.9
| FEL | 3000 | 1.5 | 2 | 1.3 | 3
| FEL | 4500 | 1.5 | 2 | 2 | 3
FEL
Skip | SKIP | 3000 | 3.5 | 1.8 | 0.8 | 6.3
| SKIP | 9000 | 3.8 | 1.8 | 1.9 | 6.84
SKIP
Hook Bin | HOOK | 15000 | 4.7 | 2.5 | 2 | 11.75
| HOOK | 30000 | 6.5 | 2.5 | 2.7 | 16.25
HOOK
Fadge | FDG | 700 | 0.8 | 0.8 | 1 | 0.64
FDG
FlexiBin® | FXB | 1000 | 1 | 1 | 1 | 1
| FXB | 2000 | 1 | 2 | 1 | 2
| FXB | 3000 | 2 | 1.5 | 1 | 3
FXB
Other | OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
OTHER
Waste Area Size
Fill in your chosen bin codes, bin sizes and bin counts as per the SEPARATION sheet. Fill in the floor area of the proposed waste storage area from the building's designs in the blue cells. Note: The proposed services on the SEPARATION sheet must be compliant i.e. Volume Serviced (L/week) must be equal to or exceed the calculated Volume Required (L/week). The Preliminary Total Floor Area (m2) for the waste storage area will be automatically created.
Bin Code | Bin Size (L) | Floor Area (m2) | Bin Count | Total Floor Area (m2)
Total Floor Area Provided in Design (m2)
Total Bin Floor Area |  |  |  | 0
Space for Bin Manoeuvres and Access |  |  |  | 0 |  |  | Preliminary Compliance | YES
Preliminary Total Floor Area |  |  |  | 0
Note: The above Preliminary Total Floor Area is a preliminary estimation, and provides the designers with an indication of the space required to store and access the waste and recovery bins. Other factors will determine the final floor area, such as: - the exact dimensions of the waste storage area (length & width) - the door (opening inward or outward) - access for wheelchair users (access to bins and turning circle) - the type of bins utilised (wheels or no wheels) - the layout of the bins - the type of vehicle servicing the waste area (Rear Load, Front Load, Box Body etc.) The exact dimensions and total floor area of the waste storage area will be unique to the building, but clear evidence must be shown that the design and layout meets storage and access requirements.

## ACCESS
Access
This section provides information on collection vehicles and their operating dimensions to be utilised to confirm suitable access is provided.
Vehicle Tracking
All vehicle tracking and access requirements must align with Waka Kotahi NZ Transport Agency - RTS 18 On road tracking curves for heavy vehicles 2007. Vehicle tracking must be done for the vehicles that will service the building. Some guidance on operating dimensions are provided below, noting that the operating dimensions of vehicles differ between waste contractors and/or councils. The exact operating dimensions of the vehicles that will be utilised for your development must be utilised for the tracking curves to confirm access, but below are indicative dimensions.
Vehicle Type | Bins Collected | Operating Dimension | Measurement | Vehicle Type | Bins Collected | Operating Dimension | Measurement
Rear End Loader | Wheelie Bins (MGB): 80L, 140L, 240L, 660L | Vehicle Driving Height | 2,690 mm | Skip | Skips: 3m3, 9m3 | Vehicle Driving Height | 3,565 mm
|  | Vehicle Loading Height | 3,088 mm |  |  | Vehicle Loading Height | 4,023 mm
|  | Vehicle Width | 2,270 mm |  |  | Vehicle Width | 2,480mm
|  | Vehicle Length | 8,166 mm |  |  | Vehicle Length | 6,967 mm
|  | Vehicle + Bin Length | 10,073 mm |  |  | Vehicle + Bin Length | 10,559 mm
|  | Turning Circle Radius | 8,500 mm |  |  | Turning Circle Radius | 8,500mm
|  | Turning Circle Diameter | 17,000 mm |  |  | Turning Circle Diameter | 17,100mm
Vehicle Type | Bins Collected | Operating Dimension | Measurement | Vehicle Type | Bins Collected | Operating Dimension | Measurement
Front End Loader | Front Load Bins (FEL): 1.5m3, 3m3, 4.5m3 | Vehicle Driving Height | 4,224 mm | Hook | Hooks: 15m3, 30m3 | Vehicle Driving Height | 3,900 mm
|  | Vehicle Loading Height | 6,199 mm |  |  | Vehicle Loading Height | 5,224 mm
|  | Vehicle Width | 2,485 mm |  |  | Vehicle Width | 2,550 mm
|  | Vehicle Length | 9,286 mm |  |  | Vehicle Length | 9,249 mm
|  | Vehicle + Bin Length | 11,582 mm |  |  | Vehicle + Bin Length | 16,607 mm
|  | Turning Circle Radius | 11,100 mm |  |  | Turning Circle Radius | 12,000 mm
|  | Turning Circle Diameter | 22,200 mm |  |  | Turning Circle Diameter | 24,000 mm
Vehicle Type | Bins Collected | Operating Dimension | Measurement | Vehicle Type | Bins Collected | Operating Dimension | Measurement
Side Loader | Wheelie Bins (MGB): 80L, 140L, 240L, 660L | Vehicle Driving Height | 3,280 mm | Box Body | Wheelie Bins (MGB): 80L, 140L, 240L, 660L | Vehicle Driving Height | 3,450 mm
|  | Vehicle Loading Height | 4,000 mm |  |  | Vehicle Width | 2,490 mm
|  | Vehicle Width | 2,482 mm |  |  | Vehicle Length | 8,630 mm
|  | Vehicle Length | 9,313 mm |  |  | Vehicle + Rear Tail Lift Length | 10,855 mm
|  | Arm Swing Clearance | 2,000 mm |  |  | Turning Circle Radius | 8,854 mm
|  | Turning Circle Radius | 11,100 mm
|  | Turning Circle Diameter | 22,200 mm

## DESIGN
Design
This section provides guidance on elements to consider and incorporate when designing a waste storage area. Although these are not minimum expectations relating to NZGBC Green Star Buildings Credit 4, it is worth noting that some of these design elements are New Zealand Building Code requirements. If consent has been provided for the building, it will be assumed that the NZBC elements have been incorporated.
Checklist | (Yes) / (No) / (N/A) | YES | No | N/A
Waste storage areas should comply with the Te Tari Kaupapa Whare Department of Building and Housing’s Compliance Document for New Zealand Building Code: Clause G15 – Solid Waste. Refer to Acceptable Solution G15/AS1.
Indoor or enclosed waste storage areas should be adequately ventilated, either by a mechanical exhaust ventilation system, or by natural ventilation to open air, in compliance with NZBC G4.
If on-site cleaning of bins is performed, a water supply tap, complying with NZBC G12 should be provided for washing down waste storage areas and applicable drainage complying with NZBC G13 should be provided. Alternatively, off-site cleaning of bins can be performed by a waste contractor.
The position and location of an external waste storage area should comply with the NZS4541:2020 sprinkler system standard. It is recommended that a qualified fire engineer is consulted to ensure your waste storage area is correctly designed, positioned and compliant with the regulations.
The waste storage area(s) should comply with the Solid Waste Bylaws of the local council, which may have specific requirements for accessibility, signage, noise, odour, hygiene, vermin control and/or security.
The floors and walls of any waste storage room should be finished with a rigid, smooth-faced impermeable surface to ensure ease of cleaning.
The dimensions of entry and exits for waste storage rooms should take the bin sizes into account, to ensure suitable access.
Adequate lighting should be provided, particularly for an enclosed storage area or room. If artificial lighting is provided for a waste storage room, switches should be located both outside and inside the room.
The waste storage area(s) should be clearly demarcated (e.g. wall, fence, painted lines) and have clear signage. This is to ensure the waste storage area(s) are clearly visible, and that only appropriate and trained personnel access the area.

## DATA
Data
Waste Generation Rates
The below waste generation rates have been calculated by utilising waste data provided by New Zealand businesses, along with the size (m2) of the gross floor area (GFA) of the entire building (including primary, secondary and tertiary spaces). Note: The NZGBC acknowledges that generation rates are not available for all building typologies, and that variations in waste generating activities within these typologies are also to be expected as these groups are very broad. To include more typology options and variations, we require more data points. If you are interested and willing to provide data for inclusion within the next version of this calculator, please email greenstarnz@nzgbc.org.nz. All data will be treated as confidential, and utilised for the sole purpose of ensuring our waste generation rate calculator is as accurate and inclusive as possible.
Building Typology | Waste Volume (L/week/100m2)
Hotel / Accommodation | 291
Aged Care | 425
Office / Admin | 304
Industrial | 428
Retail | 964
Supermarket | 1818
General / Other | 427
Waste vs Recovery Ratios
The below waste and recovery ratios have been calculated by utilising data from WM New Zealand waste audits from 2023/2024, along with 2022/2023 waste collection data totalling more than 1 million tonnes and 8.8 million cubic metres (m3) of waste and recovery services.
Waste Type | Volume %
General Waste | 30%
Recycling (Review Split Options) | 62%
Food Waste | 8%
Recycling Split Option 1 | 62% | of Total Waste
Mixed Recycling (Paper, Cardboard, Plastic Bottles, Cans, Glass) | 49% | of Total Waste
Bulky Recycling (Pallets, Polystyrene etc) | 13% | of Total Waste
Recycling Split Option 2 | 62% | of Total Waste
Mixed Recycling (Plastic Bottles, Cans, Glass) | 25% | of Total Waste
Paper & Cardboard | 24% | of Total Waste
Bulky Recycling (Pallets, Polystyrene etc) | 13% | of Total Waste
Recycling Split Option 3 | 62% | of Total Waste
Mixed Recycling (Plastic Bottles, Cans) | 23% | of Total Waste
Glass (Mixed Colours) | 2% | of Total Waste
Paper & Cardboard | 24% | of Total Waste
Bulky Recycling (Pallets, Polystyrene etc) | 13% | of Total Waste
Conversion Table
The below table provides information to assist any requirements to convert between weight (kg) and volume (L or m3):

## FAQ
Frequently Asked Questions
The below FAQs were asked during the process of creating the new NZGBC Operational Waste Calculator v1.0. It is expected that the list of FAQs related to this credit and the usage of this document will grow once the new NZGBC Green Star Buildings rating system is launched. If you would like to add a question this FAQ list, please contact the NZGBC by emailing greenstarnz@nzgbc.org.nz.
FAQs
How was the calculator built?
Building a new calculator was a lengthy and time consuming process. Firstly, we reached out to New Zealand businesses, consultancies and project management companies who have a relationship with the NZGBC and Green Star specifically (either previous or current Green Star projects). We requested historical waste data (at least 12 months) and the gross floor area for their buildings, facilities and developments, with the purpose to calculate a total volume of waste generated per week per 100m2 for different building typologies. To create this 'waste generation rate' from the data supplied to the NZGBC, some data analytics and assumptions were required, as data metrics differ and some form of data cleansing was required. In addition to the data provided to the NZGBC, the following information was used: - Data from 2022/2023 relating to waste and recycling services performed by WM New Zealand to calculate a density formula (kg/m3). Services totalling over 1 million tonnes of materials and 8.8 million cubic metres of bin volume were assessed to convert all weight data into volumetric data. - Data from 2023/2024 relating to waste characterisation audits performed by WM Sustainability Services to calculate how Total Volume of Waste can be split into a percentage of General Waste (30%), Recycling (62%) and Food Waste (8%). After combining all the above data metrics, a total volume of waste generated per week per 100m2 for different building typologies was created, which can be observed in the DATA worksheet.
Can the NZGBC provide examples of 'best practice' submissions for Credit 4 compliance?
At present, we do not have completed examples of best practice submissions. If approved, we may look to include some real submissions as examples if the project managers agree to showcase their documentation.
Can a maximum ratio of length to width be provided for the dimensions of a suitable waste storage area?
There is no exact ratio that is suitable for a waste storage area. The design, including dimensions, will be project specific, and be dependant on many factors. As an example, if the preliminary waste storage area is calculated to be 20m2, a 1m x 20m area will not be suitable, but a 3m x 7m or a 4m x 5m area would be more viable. The exact final floor area will need to consider bin type, bin size, bin count, space for access and servicing requirements, which means this is a case by case consideration.